## Features
ID | Name | Description | Status | Priority | Category | Start Date | Target Date | Completion Date | Progress % | Stakeholder Impact
auth_system | User Authentication System | Complete sign-in, registration, and user management | Completed | Critical | Core Platform | 2024-01-01 | 2024-02-15 | 2024-02-10 | 100 | Enables secure access for all users
main_dashboard | Main Dashboard | Central dashboard for procurement type selection | Completed | Critical | Core Platform | 2024-01-15 | 2024-02-20 | 2024-02-18 | 100 | Primary interface for all procurement activities
ai_tender_generator | AI Tender Generator | AI-powered tender document generation using Gemini 1.5 Flash | Completed | Critical | AI Features | 2024-02-01 | 2024-03-15 | 2024-03-10 | 100 | Automates tender creation, reducing time from days to hours
tepp_generator | AI-Enhanced TEPP Generator | Advanced TEPP generator with AI assistance | Completed | High | AI Features | 2024-02-15 | 2024-03-30 | 2024-03-25 | 100 | Streamlines evaluation process for procurement teams
contract_review | AI Contract Review System | AI-powered contract analysis and risk assessment | Completed | High | AI Features | 2024-03-01 | 2024-04-15 | 2024-04-10 | 100 | Reduces contract review time and improves accuracy
rag_system | Three-Tier RAG System | Retrieval-Augmented Generation system for compliance | Completed | Critical | AI Features | 2024-03-15 | 2024-05-01 | 2024-04-28 | 100 | Enables real-time compliance checking and document intelligence
compliance_dashboard | AI Compliance Dashboard | Real-time compliance monitoring and violation tracking | Completed | High | Compliance | 2024-04-01 | 2024-05-15 | 2024-05-10 | 100 | Ensures all procurement activities meet NSW standards
document_upload | Document Upload & Processing | Automated document processing and RAG integration | Completed | High | Document Management | 2024-04-15 | 2024-05-30 | 2024-05-25 | 100 | Automates document classification and compliance checking
quote_generator | AI Quote Generator | AI-powered quotation generation system | In Progress | Medium | AI Features | 2024-05-01 | 2024-06-15 |  | 75 | Streamlines quote creation for suppliers and contractors
historical_matching | Historical Project Matching | AI-powered matching of new projects with historical data | Planned | Medium | AI Features | 2024-06-01 | 2024-07-15 |  | 0 | Improves project planning and cost estimation accuracy

## Summary
total_features | completed_features | in_progress_features | planned_features | overall_progress_percentage | last_updated
10 | 8 | 1 | 1 | 80 | 2025-09-23T22:02:25.578807