## Features
ID | Name | Description | Status | Priority | Category | Start Date | Target Date | Completion Date | Progress % | Stakeholder Impact
auth_system | User Authentication System | Complete sign-in, registration, and user management | Completed | Critical | Core Platform | 2025-05-27 | 2025-07-11 | 2025-06-16 | 100 | Enables secure access for all users
main_dashboard | Main Dashboard | Central dashboard for procurement type selection | Completed | Critical | Core Platform | 2025-06-01 | 2025-07-16 | 2025-06-21 | 100 | Primary interface for all procurement activities
ai_tender_generator | AI Tender Generator | AI-powered tender document generation using Gemini 1.5 Flash | Completed | Critical | AI Features | 2025-06-11 | 2025-07-26 | 2025-07-06 | 100 | Automates tender creation, reducing time from days to hours
tepp_generator | AI-Enhanced TEPP Generator | Advanced TEPP generator with AI assistance | Completed | High | AI Features | 2025-06-21 | 2025-08-10 | 2025-07-16 | 100 | Streamlines evaluation process for procurement teams
contract_review | AI Contract Review System | AI-powered contract analysis and risk assessment | Completed | High | AI Features | 2025-07-01 | 2025-08-20 | 2025-07-26 | 100 | Reduces contract review time and improves accuracy
rag_system | Three-Tier RAG System | Retrieval-Augmented Generation system for compliance | Completed | Critical | AI Features | 2025-07-11 | 2025-08-30 | 2025-08-10 | 100 | Enables real-time compliance checking and document intelligence
compliance_dashboard | AI Compliance Dashboard | Real-time compliance monitoring and violation tracking | Completed | High | Compliance | 2025-07-21 | 2025-09-09 | 2025-08-25 | 100 | Ensures all procurement activities meet NSW standards
document_upload | Document Upload & Processing | Automated document processing and RAG integration | Completed | High | Document Management | 2025-07-31 | 2025-09-19 | 2025-09-09 | 100 | Automates document classification and compliance checking
quote_generator | AI Quote Generator | AI-powered quotation generation system | Completed | Medium | AI Features | 2025-09-14 | 2025-10-14 | 2025-09-24 | 100 | Streamlines quote creation for suppliers and contractors
historical_matching | Historical Project Matching | AI-powered matching of new projects with historical data | Completed | Medium | AI Features | 2025-10-09 | 2025-11-08 | 2025-09-24 | 100 | Improves project planning and cost estimation accuracy
collaborative_evaluation | Collaborative Evaluation System | AI-powered initial scoring with human committee consensus | In Progress | High | AI Features | 2025-09-24 | 2025-10-24 |  | 75 | Enables structured evaluation with AI assistance and human oversight
tepp_integration | TEPP Integration | Integrate TEPP documents and methodology into collaborative evaluation system | Planned | Critical | Integration | 2025-09-29 | 2025-10-29 |  | 0 | Ensures evaluation system follows TEPP standards and methodology
returnable_schedules | Returnable Schedules Mapping | Map supplier responses to Returnable Schedule items and validate completion | Planned | High | Integration | 2025-10-04 | 2025-11-03 |  | 0 | Aligns supplier responses with TEPP requirements
tepp_compliance | TEPP Compliance Validation | Implement TEPP compliance checking and validation against requirements | Planned | High | Compliance | 2025-10-09 | 2025-11-08 |  | 0 | Ensures all evaluations meet TEPP compliance standards
schedule_criteria_alignment | Schedule-to-Criteria Alignment | Create direct mapping between Returnable Schedule items and TEPP evaluation criteria | Planned | Medium | Integration | 2025-10-14 | 2025-11-13 |  | 0 | Links schedule items directly to evaluation criteria
tepp_structured_evaluation | TEPP Structured Evaluation | Implement TEPP-defined evaluation methodology and scoring framework | Planned | Medium | AI Features | 2025-10-19 | 2025-11-18 |  | 0 | Applies TEPP methodology to collaborative evaluation process

## Summary
total_features | completed_features | in_progress_features | planned_features | overall_progress_percentage | last_updated
16 | 10 | 1 | 5 | 62.5 | 2025-09-24T14:21:23.821096